## OHS PROJECT TOTAL
PROJECT COST ESTIMATE Project No. XXXXX
Project Information | Program Development
Project Description:
Estimate Information |  |  | OVERALL - Program Development and Implementation Cost Estimate | 651742.3
|  |  | Development Time Only | 4835.6
|  |  | TRAINING HOURS ONLY | 0
|  |  | TRAINIG COSTS ONLY | 330257.4
Does not include Refreshers Every 3 years
Date Prepared: | mm/dd/yy | Prepared By:
Cost Element Worksheet (Copyright: All Rights Reserved - Epadua)- To be used by Documented Permission Only - Not to be Shared Outside of this Course

## OHS PROGRAM POLICY
COST ELEMENT | # OF PEOPLE/EQUIPMENT | EST HOURS/COST OF ITEM | Avg SALARY | BASE ESTIMATE | CONTINGENCY |  | TOTAL ESTIMATE
[5 empty] | % | $
RESOURCES REQUIRED TO DEVELOP THE POLICY
HUMAN RESOURCES TIME(ESTIMATES OR AVERAGE ONLY)
Management/Supervisor | 1 | 8 | 75 | 600 | 10% | 60 | 660
Workers |  |  |  | 0 | 10% | 0 | 0
Committee Member |  |  |  | 0 | 10% | 0 | 0
HR RESOURCE TIME COST SUBTOTAL |  |  |  | 600 | 10% | 60 | 660
EQUIPMENT REQUIRED TO PRIOR TO IMPLEMENTATION
Type: first aid kits |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
EQUIPMENT COST SUBTOTAL |  |  |  | 0 |  | 0 | 0
RESOURCES COST TOTAL (Development and Equipment) |  |  |  | 0 |  | 0 | 0
RESOURCES FOR TRAINING - PEOPLE AND TIME (REVIEW TRAINING MATRIX)
MANAGEMENT | 1 | 50 | 75 | 3750 | 10% | 375 | 4125
SUPERVISORS | 6 | 50 | 35 | 10500 | 10% | 1050 | 11550
WORKERS | 100 | 10 | 18 | 18000 | 10% | 1800 | 19800
WSH COMMITTEE MEMBERS | 6 | 74 | 26 | 11544 | 10% | 1154.4 | 12698.4
OTHER (EXTERNAL CONSULTANT/TRAINER) |  |  |  | 0 | 10% | 0 | 0
TRAINING PLAN COSTS |  |  |  | 43794 |  | 4379.4 | 48173.4
POLICY/PROCEDURE MAINTENANCE
DATA ENTRY/RECORD KEEPING - HUMAN RESOURCES (MAY BE A ONE TIME COSTS FOR THE WHOLE PROGRAM) | 1 | 2184 | 18 | 39312 | 10% | 3931.2 | 43243.2
OTHER - STORAGE OF DOCUMENTS/RECORDS WHERE APPLLICABLE - CAN BE ONE TIME FOR THE PROGRAM) |  |  |  | 0 | 10% | 0 | 0
POLICY/PROCEDURE MAINTENANCE COSTS |  |  |  | 39312 |  | 3931.2 | 43243.2
OTHER COSTS TO CONSIDER:
<INSERT ITEMS> |  |  |  | 0 | 10% | 0 | 0
<INSERT ITEMS> |  |  |  | 0 | 10% | 0 | 0
<INSERT ITEMS> |  |  |  | 0 | 10% | 0 | 0
OTHER COSTS TOTAL |  |  |  | 0 |  | 0 | 0
TOTAL |  |  |  | 83106 |  | 8310.6 | 91416.6

## HRC POLICY
COST ELEMENT | # OF PEOPLE/EQUIPMENT | EST HOURS/COST OF ITEM | Avg SALARY | BASE ESTIMATE | CONTINGENCY |  | TOTAL ESTIMATE
[5 empty] | % | $
RESOURCES REQUIRED TO DEVELOP THE POLICY
HUMAN RESOURCES TIME(ESTIMATES OR AVERAGE ONLY)
Management/Supervisor | 1 | 8 | 74 | 592 | 10% | 59.2 | 651.2
Workers |  |  |  | 0 | 10% | 0 | 0
Committee Member | 6 | 3 | 26 | 468 | 10% | 46.8 | 514.8
HR RESOURCE TIME COST SUBTOTAL |  |  |  | 1060 | 10% | 106 | 1166
EQUIPMENT REQUIRED TO PRIOR TO IMPLEMENTATION
Type:Investigation Tool Kit | 5 | 500 |  | 2500 | 10% | 250 | 2750
Type:inspection Tool kit | 10 | 500 |  | 5000 | 10% | 500 | 5500
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
EQUIPMENT COST SUBTOTAL |  |  |  | 7500 |  | 750 | 8250
RESOURCES COST TOTAL (Development and Equipment) |  |  |  | 7500 |  | 750 | 8250
RESOURCES FOR TRAINING - PEOPLE AND TIME (REVIEW TRAINING MATRIX)
MANAGEMENT | 1 | 20 | 75 | 1500 | 10% | 150 | 1650
SUPERVISORS | 6 | 20 | 35 | 4200 | 10% | 420 | 4620
WORKERS | 100 | 20 | 18 | 36000 | 10% | 3600 | 39600
WSH COMMITTEE MEMBERS | 6 | 50 | 26 | 7800 | 10% | 780 | 8580
OTHER (EXTERNAL CONSULTANT/TRAINER) |  |  |  | 0 | 10% | 0 | 0
TRAINING PLAN COSTS |  |  |  | 49500 |  | 4950 | 54450
POLICY/PROCEDURE MAINTENANCE
DATA ENTRY/RECORD KEEPING - HUMAN RESOURCES (MAY BE A ONE TIME COSTS FOR THE WHOLE PROGRAM) |  |  |  | 0 | 10% | 0 | 0
OTHER - STORAGE OF DOCUMENTS/RECORDS WHERE APPLLICABLE - CAN BE ONE TIME FOR THE PROGRAM) |  |  |  | 0 | 10% | 0 | 0
POLICY/PROCEDURE MAINTENANCE COSTS |  |  |  | 0 |  | 0 | 0
OTHER COSTS TO CONSIDER:
<INSERT ITEMS> |  |  |  | 0 | 10% | 0 | 0
<INSERT ITEMS> |  |  |  | 0 | 10% | 0 | 0
<INSERT ITEMS> |  |  |  | 0 | 10% | 0 | 0
OTHER COSTS TOTAL |  |  |  | 0 |  | 0 | 0
TOTAL |  |  |  | 57000 |  | 5700 | 62700

## EMERGENCY PREPAREDNESS
COST ELEMENT | # OF PEOPLE/EQUIPMENT |  | Avg SALARY | BASE ESTIMATE | CONTINGENCY |  | TOTAL ESTIMATE
|  | EST HOURS/COST OF ITEM |  |  | % | $
RESOURCES REQUIRED TO DEVELOP THE POLICY
HUMAN RESOURCES TIME(ESTIMATES OR AVERAGE ONLY)
Management/Supervisor | 1 | 8 | 75 | 600 | 10% | 60 | 660
Workers |  |  |  | 0 | 10% | 0 | 0
Committee Member | 6 | 2 | 26 | 312 | 10% | 31.2 | 343.2
HR RESOURCE TIME COST SUBTOTAL |  |  |  | 912 | 10% | 91.2 | 1003.2
EQUIPMENT REQUIRED TO PRIOR TO IMPLEMENTATION
|  |  |  | 0 | 10% | 0 | 0
Type: Signs for Extinguishers | 9 | 20 |  | 180 | 10% | 18 | 198
Type: Muster Point Signs | 3 | 40 |  | 120 | 10% | 12 | 132
Type: Floor Plan Signs | 9 | 63 |  | 567 | 10% | 56.7 | 623.7
Type: First-Aid Kits | 4 | 360 |  | 1440 | 10% | 144 | 1584
Type: Two-Way Radio | 2 | 150 |  | 300 | 10% | 30 | 330
Type: Eye-wash Stations | 9 | 420 |  | 3780 | 10% | 378 | 4158
Type: Panic/Escape Room | 3 | 50000 |  | 150000 | 10% | 15000 | 165000
Type: Intercom System | 1 | 10000 |  | 10000 | 10% | 1000 | 11000
Type: Plumber | 8 | 100 |  | 800 | 10% | 80 | 880
Type: First Aid Room (See MB WSH Reg Pt 5, Schedule C for content) | 1 | 10250 |  | 10250 | 10% | 1025 | 11275
Type: First Aid Room Signs | 9 | 40 |  | 360 | 10% | 36 | 396
Type: |  |  |  | 0 | 10% | 0 | 0
EQUIPMENT COST SUBTOTAL |  |  |  | 177797 |  | 17779.7 | 195576.7
RESOURCES COST TOTAL (Development and Equipment) |  |  |  | 177797 |  | 17779.7 | 195576.7
RESOURCES FOR TRAINING - PEOPLE AND TIME (REVIEW TRAINING MATRIX)
MANAGEMENT | 1 | 36 | 75 | 2700 | 10% | 270 | 2970
SUPERVISORS | 6 | 36 | 35 | 7560 | 10% | 756 | 8316
WORKERS | 100 | 20 | 18 | 36000 | 10% | 3600 | 39600
WSH COMMITTEE MEMBERS | 6 | 40 | 26 | 6240 | 10% | 624 | 6864
OTHER (EXTERNAL CONSULTANT/TRAINER) | 3 | 60 | 100 | 18000 | 10% | 1800 | 19800
TRAINING PLAN COSTS |  |  |  | 70500 |  | 7050 | 77550
POLICY/PROCEDURE MAINTENANCE
DATA ENTRY/RECORD KEEPING - HUMAN RESOURCES (MAY BE A ONE TIME COSTS FOR THE WHOLE PROGRAM) |  |  |  | 0 | 10% | 0 | 0
OTHER - STORAGE OF DOCUMENTS/RECORDS WHERE APPLLICABLE - CAN BE ONE TIME FOR THE PROGRAM) |  |  |  | 0 | 10% | 0 | 0
POLICY/PROCEDURE MAINTENANCE COSTS |  |  |  | 0 |  | 0 | 0
OTHER COSTS TO CONSIDER:
<INSERT ITEMS> |  |  |  | 0 | 10% | 0 | 0
<INSERT ITEMS> |  |  |  | 0 | 10% | 0 | 0
<INSERT ITEMS> |  |  |  | 0 | 10% | 0 | 0
OTHER COSTS TOTAL |  |  |  | 0 |  | 0 | 0
TOTAL |  |  |  | 248297 |  | 24829.7 | 273126.7

## CHEM BIO PLAN
COST ELEMENT |  |  |  | BASE ESTIMATE | CONTINGENCY |  | TOTAL ESTIMATE | COST ELEMENT | # OF PEOPLE/EQUIPMENT | EST HOURS/COST OF ITEM | Avg SALARY | BASE ESTIMATE | CONTINGENCY |  | TOTAL ESTIMATE
| # OF PEOPLE/EQUIPMENT | EST HOURS/COST OF ITEM | Avg SALARY |  | % | $ | [6 empty] | % | $
RESOURCES REQUIRED TO DEVELOP THE POLICY | [7 empty] | RESOURCES REQUIRED TO DEVELOP THE POLICY
HUMAN RESOURCES TIME(ESTIMATES OR AVERAGE ONLY) | [7 empty] | HUMAN RESOURCES TIME(ESTIMATES OR AVERAGE ONLY)
Management/Supervisor |  |  |  | 0 | 10% | 0 | 0 | Management/Supervisor | 1 | 8 | 75 | 600 | 10% | 60 | 660
Workers |  |  |  | 0 | 10% | 0 | 0 | Workers |  |  |  | 0 | 10% | 0 | 0
Committee Member |  |  |  | 0 | 10% | 0 | 0 | Committee Member | 6 | 2 | 26 | 312 | 10% | 31.2 | 343.2
HR RESOURCE TIME COST SUBTOTAL |  |  |  | 0 | 10% | 0 | 0 | HR RESOURCE TIME COST SUBTOTAL |  |  |  | 912 | 10% | 91.2 | 1003.2
EQUIPMENT REQUIRED TO PRIOR TO IMPLEMENTATION |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0 | EQUIPMENT REQUIRED TO PRIOR TO IMPLEMENTATION
Type: |  |  |  | 0 | 10% | 0 | 0 | Type: Chemical-Resistant Gloves | 200 | 6 |  | 1200 | 10% | 120 | 1320
Type: |  |  |  | 0 | 10% | 0 | 0 | Type:Chemical Resistant Googles | 200 | 3 |  | 600 | 10% | 60 | 660
Type: |  |  |  | 0 | 10% | 0 | 0 | Type: Chemical-Resistant Aprons | 100 | 25 |  | 2500 | 10% | 250 | 2750
Type: |  |  |  | 0 | 10% | 0 | 0 | Type: Respirators | 100 | 200 |  | 20000 | 10% | 2000 | 22000
Type: |  |  |  | 0 | 10% | 0 | 0 | Type: Respirator Filters | 200 | 50 |  | 10000 | 10% | 1000 | 11000
Type: |  |  |  | 0 | 10% | 0 | 0 | Type: Chemical Spill Kits | 9 | 150 |  | 1350 | 10% | 135 | 1485
Type: |  |  |  | 0 | 10% | 0 | 0 | Type: Chemical Storage Containers | 4 | 500 |  | 2000 | 10% | 200 | 2200
Type: |  |  |  | 0 | 10% | 0 | 0 | Type: Hazardous Waste Cage | 1 | 800 |  | 800 | 10% | 80 | 880
Type: |  |  |  | 0 | 10% | 0 | 0 | Type: PPE Vending Machines | 6 | 3000 |  | 18000 | 10% | 1800 | 19800
Type: |  |  |  | 0 | 10% | 0 | 0 | Type: Chemical Spill Pallets | 3 | 500 |  | 1500 | 10% | 150 | 1650
Type: |  |  |  | 0 | 10% | 0 | 0 | Type: Chemical Transport Cart | 2 | 400 |  | 800 | 10% | 80 | 880
Type: |  |  |  | 0 | 10% | 0 | 0 | Type: TDG Placards Package | 3 | 300 |  | 900 | 10% | 90 | 990
EQUIPMENT COST SUBTOTAL |  |  |  | 0 |  | 0 | 0 | Type: Hazardous Waste Drums | 4 | 250 |  | 1000 | 10% | 100 | 1100
RESOURCES COST (DEVELOPMENT) TOTAL |  |  |  | 0 |  | 0 | 0 | EQUIPMENT COST SUBTOTAL |  |  |  | 60650 |  | 6065 | 66715
[8 empty] | RESOURCES COST TOTAL (Development and Equipment) |  |  |  | 60650 |  | 6065 | 66715
RESOURCES FOR TRAINING - PEOPLE AND TIME (REVIEW TRAINING MATRIX)
MANAGEMENT | [7 empty] | RESOURCES FOR TRAINING - PEOPLE AND TIME (REVIEW TRAINING MATRIX)
SUPERVISORS |  |  |  | 0 | 10% | 0 | 0 | MANAGEMENT | 1 | 30 | 75 | 2250 | 10% | 225 | 2475
WORKERS |  |  |  | 0 | 10% | 0 | 0 | SUPERVISORS | 6 | 40 | 35 | 8400 | 10% | 840 | 9240
WSH COMMITTEE MEMBERS |  |  |  | 0 | 10% | 0 | 0 | WORKERS | 100 | 40 | 18 | 72000 | 10% | 7200 | 79200
OTHER (EXTERNAL CONSULTANT/TRAINER) |  |  |  | 0 | 10% | 0 | 0 | WSH COMMITTEE MEMBERS | 6 | 40 | 26 | 6240 | 10% | 624 | 6864
TRAINING PLAN COSTS |  |  |  | 0 |  | 0 | 0 | OTHER (EXTERNAL CONSULTANT/TRAINER) |  |  |  | 0 | 10% | 0 | 0
[8 empty] | TRAINING PLAN COSTS |  |  |  | 86640 |  | 8664 | 95304
POLICY/PROCEDURE MAINTENANCE
DATA ENTRY/RECORD KEEPING - HUMAN RESOURCES (MAY BE A ONE TIME COSTS FOR THE WHOLE PROGRAM) |  |  |  | 0 | 10% | 0 | 0 | POLICY/PROCEDURE MAINTENANCE
OTHER - STORAGE OF DOCUMENTS/RECORDS WHERE APPLLICABLE - CAN BE ONE TIME FOR THE PROGRAM) |  |  |  | 0 | 10% | 0 | 0 | DATA ENTRY/RECORD KEEPING - HUMAN RESOURCES (MAY BE A ONE TIME COSTS FOR THE WHOLE PROGRAM) |  |  |  | 0 | 10% | 0 | 0
POLICY/PROCEDURE MAINTENANCE COSTS |  |  |  | 0 |  | 0 | 0 | OTHER - STORAGE OF DOCUMENTS/RECORDS WHERE APPLLICABLE - CAN BE ONE TIME FOR THE PROGRAM) |  |  |  | 0 | 10% | 0 | 0
[8 empty] | POLICY/PROCEDURE MAINTENANCE COSTS |  |  |  | 0 |  | 0 | 0
OTHER COSTS TO CONSIDER:
<INSERT ITEMS> |  |  |  | 0 | 10% | 0 | 0 | OTHER COSTS TO CONSIDER:
<INSERT ITEMS> |  |  |  | 0 | 10% | 0 | 0 | <INSERT ITEMS> |  |  |  | 0 | 10% | 0 | 0
<INSERT ITEMS> |  |  |  | 0 | 10% | 0 | 0 | <INSERT ITEMS> |  |  |  | 0 | 10% | 0 | 0
OTHER COSTS TOTAL |  |  |  | 0 |  | 0 | 0 | <INSERT ITEMS> |  |  |  | 0 | 10% | 0 | 0
[8 empty] | OTHER COSTS TOTAL |  |  |  | 0 |  | 0 | 0
[8 empty] | TOTAL |  |  |  | 147290 |  | 14729 | 162019

## TRAINING POLICY
COST ELEMENT | # OF PEOPLE/EQUIPMENT | EST HOURS/COST OF ITEM | Avg SALARY | BASE ESTIMATE | CONTINGENCY |  | TOTAL ESTIMATE
[5 empty] | % | $
RESOURCES REQUIRED TO DEVELOP THE POLICY
HUMAN RESOURCES TIME(ESTIMATES OR AVERAGE ONLY)
Management/Supervisor | 1 | 8 | 75 | 600 | 10% | 60 | 660
Workers |  |  |  | 0 | 10% | 0 | 0
Committee Member | 6 | 2 | 26 | 312 | 10% | 31.2 | 343.2
HR RESOURCE TIME COST SUBTOTAL |  |  |  | 912 | 10% | 91.2 | 1003.2
EQUIPMENT REQUIRED TO PRIOR TO IMPLEMENTATION
Type: Computers | 10 | 200 |  | 2000 | 10% | 200 | 2200
Type: Computer Software | 1 | 5000 |  | 5000 | 10% | 500 | 5500
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
Type: |  |  |  | 0 | 10% | 0 | 0
EQUIPMENT COST SUBTOTAL |  |  |  | 7000 |  | 700 | 7700
RESOURCES COST TOTAL (Development and Equipment) |  |  |  | 7000 |  | 700 | 7700
RESOURCES FOR TRAINING - PEOPLE AND TIME (REVIEW TRAINING MATRIX)
MANAGEMENT | 1 | 36 | 75 | 2700 | 10% | 270 | 2970
SUPERVISORS | 6 | 36 | 35 | 7560 | 10% | 756 | 8316
WORKERS | 100 | 20 | 18 | 36000 | 10% | 3600 | 39600
WSH COMMITTEE MEMBERS | 6 | 40 | 26 | 6240 | 10% | 624 | 6864
OTHER (EXTERNAL CONSULTANT/TRAINER) |  |  |  | 0 | 10% | 0 | 0
TRAINING PLAN COSTS |  |  |  | 49800 |  | 4980 | 54780
POLICY/PROCEDURE MAINTENANCE
DATA ENTRY/RECORD KEEPING - HUMAN RESOURCES (MAY BE A ONE TIME COSTS FOR THE WHOLE PROGRAM) |  |  |  | 0 | 10% | 0 | 0
OTHER - STORAGE OF DOCUMENTS/RECORDS WHERE APPLLICABLE - CAN BE ONE TIME FOR THE PROGRAM) |  |  |  | 0 | 10% | 0 | 0
POLICY/PROCEDURE MAINTENANCE COSTS |  |  |  | 0 |  | 0 | 0
OTHER COSTS TO CONSIDER:
<INSERT ITEMS> |  |  |  | 0 | 10% | 0 | 0
<INSERT ITEMS> |  |  |  | 0 | 10% | 0 | 0
<INSERT ITEMS> |  |  |  | 0 | 10% | 0 | 0
OTHER COSTS TOTAL |  |  |  | 0 |  | 0 | 0
TOTAL |  |  |  | 56800 |  | 5680 | 62480